## Slide 1
Florida Power & Light
Performance Process Review & Assessment
Proposal
Nov 2017

## Slide 2: Table of Contents
Our Understanding
Scope
Approach
Deliverables
Tool Requirements
Assumptions
Dependencies
Timeline & Resources
Case Study

## Slide 3: Our Understanding
  FPL has undergone Digital Customer Experience Redesign program to ensure the functionality to be available to its customers on Mobile Phones, Tablets and Desktops
  The rollout was very successful ensuring increased traffic to FPL.com from these devices
  With the current deployment architecture the FPL.com was able to handle regular day workload with no trouble
  Performance and/or Availability issues in FPL.com were observed when hurricane Irma hit Florida resulting in power cut for majority of FPL customers across Florida
  End users(customers) were trying to access “Outage” and/or “Account Management” application from Mobiles/Tablets/Desktops in large numbers which resulted in application “failures”
  Performance testing done prior to Irma situation was based on the production workload model, however in this case the workload was skewed in favor of just a couple of flows
  Cognizant’s objective is to assess performance scalability and availability of these applications by reviewing the workload, architecture, processes, capacity and provide recommendations so that such downtimes are avoided in future by augmenting to the work done with current partners in the area of workload modelling

## Slide 4: Scope
In Scope Activities | Out of Scope | 
Kick-off meeting with key stakeholders on the drivers for assessment & set expectations Meet with stakeholders to gather & understand the following Critical transactions, Functional and Non-Functional Requirements (NFR) Performance strategy - environment & monitoring set up, Deployment Architecture Perform the assessment in a two phase approach – Analyze historical production issues and review ongoing performance testing and provide recommendations Assess the following collated details: Performance testing conducted for Outage and Account Management application. Analyze reports and workload characterization simulated Analyze other applications like PEARL as applicable and plan a holistic performance test Utilize the existing workload model (complete or with modifications) derived during IRMA situation and work with performance testing for simulation and use test data with new tools as applicable Analyze the key production resource metrics during the period of performance issue to validate the capacity available, including mainframe Understand the tools available for Monitoring, Performance Testing, Profiling, APM and Mainframe Identify the bottlenecks and provide recommendations Identify candidate transactions(if any) for tuning and provide inputs to dev team. Deliver assessment report including key observations, hotspots/risks and recommendations | Assessment of any external interfaces or 3rd party components and enterprise shared infrastructure Assessment of any applications other than Outage and Account Management Planning, preparation and execution of any testing Actual Implementation of recommendations provided | 

## Slide 5: Approach
Meet with stakeholders & Gather to finalize focus areas for assessment
As-IS Implementation roadmap, Application Setup and Modules, Application interfaces & integration, Flows, Workload, Documentation Status, Analyze historical performance issues, existing PE tools available
Critical transactions, deployment architecture & configurations
Performance strategy including NFR definition, performance testing, environment & monitoring set up
Go Live Plan & Readiness : NFR, SLA, BCP and DR strategy , Release and Change Process, Performance test results, Open risks and defects
Tools landscape and workload characterization
Assess Outage and Account Management deployment Architecture, Change and Release Management
Assess baseline NFR and performance strategy
Assess performance test results including server capacity usage, JVM heap usage
Plan performance tests with revised workload model in the QA environment – baseline measurement and with post tuning
Application process reengineering with development team and APM
Application profiling with development team
Total Duration – 4 weeks
  Deliver Assessment Report including
Key Observations on
  Recomendations to improve application scalability and performance to achive peak loads
  Process to assess performance impact for new applications
  Server capacity usage from performance tests results
  NFR’s, PE Tools
Provide recommendations for identified performance issues/risks identified in deployment configurations (JVM heap), integration architecture
Provide implementation roadmap as short/long term recommendations
Gather
Assess
Recommend
Application Performance Assessment
Key Activities

## Slide 6: Deliverables
Deliverable | Description
Weekly Status Report | Scope refinement (by end of 1st week) Weekly Progress updates Plan for next week Key observations, hotspots Issues & Dependencies
Performance Assessment Report | Key observations on Identification of Performance and scalability bottlenecks in current version application in Production Environment Root cause of the bottlenecks NFRs Provide recommendations for identified performance issues/risks identified in deployment configurations, integration architecture Provide implementation roadmap as short/long term recommendations

## Slide 7: Tool Requirements
Analysis Focus Area | Tool / Report Name | Tool Type
Server resource capacity utilization trend analysis (CPU, Memory, Disk & Network I/O) | vmstat & iostat (IBM AIX) | Native Tools
Web/Http server | Web/Http access logs | Web access logs
Websphere Application Server utilization monitoring (Threads, Connections, Heap usage) | Websphere Admin Console | IBM Owned
DB2, Oracle (Mobile database server) | AWR report, Transaction workload reports | Native Tool
JVM heap usage analysis | GC Viewer / IBM PMAT | Open Source / Freeware
Performance Test reports | Performance test execution reports from the tool | Commercial / Native Tools
UNIX vmstat logs analysis | Analyzer Studio | Cognizant Proprietary Tool
Web/Http Access Logs analysis | Web Log Analyzer | Cognizant Proprietary Tool
Transaction call tree, Profiling in QA | IT CAM | APM
Note:
Cognizant has provided indicative list of focus areas and tools/reports required for the assessment
Cognizant will leverage the equivalent tools/reports available in FPL and will align the ‘Assess’ phase activities based on availability of reports/logs
Access to all these tools to be provided in week1 Phase

## Slide 8: Assumptions
Category | Key Assumptions
Effort Estimate & Project Schedule | Effort estimate is based on the current understanding of the requirements. Any extension or change in scope would result in appropriate revisions in effort and timelines.
Infrastructure, Environment & Tools | FPL will provide desktop/laptop, LAN ID to access network and required licenses to tools FPL will provide necessary access to applications, databases/data, documents, reports and environments configurations FPL will provide necessary approvals to use any Cognizant proprietary tools
Support & Availability of FPL resources | FPL will ensure following key stakeholders available during the assessment – Single Point of Contact (PM), Business Analyst, Enterprise & Application Architects, Development Lead, QA Performance Test Leads, Infrastructure Support wherever existing Cognizant resources could not be leveraged
Business Analyst | Non-Functional requirements and critical transaction details will be provided
Enterprise & Application Architects | End-End deployment architecture & design details and known architecture risks/limitations will be given Non-Functional requirements for peak load conditions will be provided – Metrics during the production peak load would be provided. Critical components in the deployment and configuration details will be provided Support from the existing Cognizant resources on the field would be availed
QA Performance Testing | Performance test results will include data from testing tool and server performance monitoring metrics (e.g. CPU, Memory, I/O usage, JVM usage, Connection pools, database performance metrics) Performance test scenario, test results and summary documents will be provided in 1st week Performance testing team will execute tests if any required to collect more monitoring data Production and performance test environment configurations comparison details will be provided including data volume

## Slide 9: Dependencies
Existing Cognizant team would be leveraged for Coordination (SPOC), Enterprise Application Architecture, Development and QA support during entire duration
Support hours requested are indicative for planning purpose and any additional meeting will be scheduled with prior notification
Additional support may be required from QA performance testing team to execute tests if any needed for real time analysis
Stakeholders | Activity | Mode of Communication | Duration in hours |  | What is Expected
 |  |  | Gather Phase | Assess & Recommend Phase | 
Senior Management | Project Kickoff Meeting | Meeting | 1 |  | Define objectives, scope, set expectations
 | Final Presentation | Meeting/ Discussions |  | 2 | Feedback on the assessment report
 |  |  |  |  | Future course of action / next steps
Functional/Business | NFR Elucidation | Discussions / Meeting | 4 hours/week | 1 hour / week | Provide business drivers & objectives
SMEs |  |  |  |  | Provide details users, roles, geographic distribution & access
 |  |  |  |  | Details about business NFR, Growth forecasts
Infrastructure / Systems Support (Jaime Warren) | Infrastructure inventory & configurations, monitoring | Discussion / Document / email | 4 hours / week | 1 hour / week | Commission the IT CAM tool in the QA environment
 |  |  |  |  | Provide the require reports from WAS, Mainframes production during IRMA situation. Details on utilizations to be shared
 |  |  |  |  | Details about maintenance schedule, backup, down time, etc. Provision a QA environment which is similar to the production environment in terms of factor and deployment architecture

## Slide 10: Timeline & Resources
Phases | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10
Phase 1 - Review process and Historical Issue |  |  |  |  |  |  |  |  |  | 
Gather |  |  |  |  |  |  |  |  |  | 
Assess |  |  |  |  |  |  |  |  |  | 
Recommend & Report |  |  |  |  |  |  |  |  |  | 
Phase 2 - Performance Assessment |  |  |  |  |  |  |  |  |  | 
Gather |  |  |  |  |  |  |  |  |  | 
Assess |  |  |  |  |  |  |  |  |  | 
Recommend & Report |  |  |  |  |  |  |  |  |  | 
Offshore – Lead Architect | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Offshore – Sr. Performance Engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 11
Case Study – Performance CoE
Cognizant experience in a PE services rollout engagement
Customer Situation
Performance Testing is engaged very late in release cycle and impacts release timeline when performance issues are detected
No in-depth analysis and RCA during development & performance testing deferred risks to production
Continuous build delivery platform is implemented and no process to address performance objectives early in build
Cognizant’s Solution
Cognizant proposed 3 phase approach to met customer objectives
  Assessment [Assess current state for strengths & gaps, define roadmap for target state]
  Pilot PE capabilities [Shift-Left practices such as NFR analysis, UI & Code Profiling, Early Performance Test for services in CI]
  PE rollout [Rollout PE practices in releases and continuous improvement]
NFR analysis using production logs ensure right at the first time in terms of NFR clarity & quality
Established risk assessment based PE scope that helped to reduce full scale performance tests in releases
Integrated UI Profiling, Java Code Profiling & SQL analysis in agile iterations to address performance issues in build
Enhanced performance monitoring strategy using APM tools for effective RCA
Optimized UI transactions and batch performance
Change Management
Established steering committee to communicate to stakeholders
Leveraged agile coach to budget for technical stories in agile iterations to address performance NFR
Quality gate introduced to review & agree on risk based PE scope and review results
Accomplishments
Key Challenges
Lack of ownership & accountability in delivery roles to address NFR in development life cycle
Motivate/incentivize stakeholders to participate PE initiative and adopt
Lack of effort & time from stakeholders for interview and to share application knowledge

## Slide 12: Thank You